## Project Plan
At Risk | Task ID | Task Name | Start Date | End Date | Dependencies | Duration | % Complete | Comments
| 1 | Initial works
| 1.1 | Reseaching ideas and Project selection | Not Applicable |  |  |  | 100% | This tasks are now completed.
| 1.2 | Getting supervisor's approval on project idea
| 1.3 | Hands on RMI technology, fixing & resolving technical issues, research, working on various tutorials, getting a basic working application
| 2 | Proposal, Literature Review and Initial Report | 2014-07-01 | 2014-07-08 |  | 9 | 100% | Project Title: Investigation of security implications of Java RMI.
| 2.1 | Proposal and planning | 2014-07-01 | 2014-07-02 |  | 2 | 100%
| 2.2 | Submission of proposal | 2014-07-03 | 2014-07-03 | 2.1 | 1 | 100%
| 2.3 | RMI Technology background research and documentation + upload on Project Portal | 2014-07-04 | 2014-07-07 | 2.2 | 4 | 100% | Background Research + a brief analysis of the history of RMI-specific exploits publically released (check public databases for this - and put them in a nice table, classifying them possibly in different categories and showing numbers and trends)
| 2.4 | Feedback from Supervisor (Afternoon session would be helpful) | 2014-07-07 | 2014-07-07 |  | 1 | 100% | A literature focused feedback at this stage will be regarded very beneficial and would help me: 1. Identify and close any gaps in RMI technology based research and documentation 2. Gauge the depth of research and documentation needed for security analysis 3. Discuss the appropriateness of the planned testbed prototype application
| 2.5 | Reflection & Evaluation of the feedback and implementing any suggestion | 2014-07-08 | 2014-07-09 |  | 1 | 100%
| 3 | Analysis of RMI security aspects | 2014-07-10 | 2014-08-28 |  | 18 | 83.33%
| 3.1 | RMI security focused literature review and documentation | 2014-07-10 | 2014-07-20 |  | 11 | 50% | ACM and IEEE mainly. Divide into: RMI vulnerabilities and poor implementation of RMI vulnerabilities.
| 3.2 | Feedback from Supervisor | 2014-07-21 | 2014-07-21 |  | 1 | 100% | Need to discuss what exploitation and experiments can be carried out: 1. What to be achieved? 2. How to demostrate this achivement? 3. Revisit the planned testbed prototype application
| 3.3 | Reflection & Evaluation of the feedback and implementing any suggestion | 2014-07-22 | 2014-07-28 |  | 6 | 100%
| 4 | Testbed prototype development | 2014-08-01 | 2014-08-19 |  | 19 | 50%
| 4.1 | Prototype Application and GUI layer | 2014-08-01 | 2014-08-07 |  | 7 | 100% | Currently the plan is to write a simple program that carries out various exhuastive calculations with different number of threads and gauges the performance for lapsed time. This application will measure whether increasing number of threads will increase performance for a given task.
| 4.2 | Feedback from Supervisor (Afternoon session due to other appointments in the morning) | 2014-08-08 | 2014-08-08 |  | 1 | 0% | Feedback here may be focused on: 1. How the application serves the purpose 2. What can be done to cause a security vulnerability and exploit it
| 4.3 | Adding security vulnerability code to the Client Side | 2014-08-09 | 2014-08-10 |  | 2 | 100% | Client application will try to access user areas on the Server side
| 4.4 | Exploitation of security vulnerability | 2014-08-11 | 2014-08-12 |  | 2 | 100%
| 4.5 | Feedback from Supervisor | 2014-08-13 | 2014-08-13 |  | 1 | 0% | Discuss the findings, what and what not went well, how to present this effectively.
| 4.6 | Documentation | 2014-08-14 | 2014-08-19 |  | 6 | 0%
| 5 | Report Writing | 2014-08-20 | 2014-09-02 |  | 13 | 0%
| 5.1 | Consolidation of documentations | 2014-08-20 | 2014-08-22 |  | 3 | 0%
| 5.2 | Reviewing and Critical evaluation: what worked well and what didn't | 2014-08-23 | 2014-08-26 |  | 4 | 0%
| 5.3 | Evaluation of strengths and weakness | 2014-08-27 | 2014-08-28 |  | 2 | 0%
| 5.4 | Future works | 2014-08-29 | 2014-08-29 |  | 1 | 0%
| 5.5 | Tidying up, referencing and finalising report | 2014-08-30 | 2014-09-02 |  | 3 | 0%