## MSc Project
At Risk | Task ID | Task Name | Start Date | End Date | Dependencies | Duration | % Complete | Comments
| 1 | Researching ideas and project selection | 2013-09-23 | 2013-11-30 |  | 20 | 100%
| 1.1 | Exploring security issues in Mobile platform | 2013-09-23 | 2013-11-03 |  | 13 | 100%
| 1.2 | Investigating project ideas in other areas | 2013-11-09 | 2013-11-24 |  | 6 | 100%
| 1.3 | Project selection | 2013-11-30 | 2013-11-30 | 1.1, 1.2 | 1 | 100%
| 2 | Proposal, Literature Review and Initial Report | 2013-11-25 | 2013-12-22 |  | 9 | 29% | Project Title: Investigation of security implications of Java RMI.
| 2.1 | Proposal and planning | 2013-12-15 | 2013-12-21 | 1.3FS +4 days | 2 | 40%
| 2.2 | Meeting supervisor for feedback | 2013-12-18 | 2013-12-18 |  | 1
| 2.3 | Initial literature review and documentation | 2013-11-25 | 2013-12-22 |  | 9 | 30%
| 3 | Application Development | 2013-12-23 | 2014-03-02 |  | 21
| 3.1 | Coding and Testing of a simple application | 2013-12-23 | 2014-01-18 |  | 8
| 3.2 | Meeting supervisor for feedback on application | 2014-01-13 | 2014-01-13 |  | 1
| 3.3 | Enhancement and extension coupled with testing | 2014-01-17 | 2014-02-09 |  | 9
| 3.4 | Documentation | 2014-02-15 | 2014-03-02 |  | 6
| 4 | Analysis of security aspects | 2014-03-08 | 2014-04-13 |  | 12
| 4.1 | Literature review and documentation | 2014-03-08 | 2014-03-16 |  | 4
| 4.2 | Exploitation of security vulnerability | 2014-03-22 | 2014-03-30 |  | 4
| 4.3 | Documentation | 2014-04-05 | 2014-04-13 |  | 4
| 5 | Report Writing | 2014-04-15 | 2014-05-18 |  | 11
| 5.1 | Consolidation of documentations | 2014-04-15 | 2014-04-20 |  | 3
| 5.2 | Reviewing and Critical evaluation: what worked well and what didn't | 2014-04-26 | 2014-04-27 |  | 2
| 5.3 | Evaluation of strengths and weakness | 2014-05-03 | 2014-05-03 |  | 1
| 5.4 | Future works | 2014-05-04 | 2014-05-04 |  | 1
| 5.5 | Tidying up, referencing and finalising report | 2014-05-10 | 2014-05-18 |  | 4